School Improvement/ASSIST Language for those schools participating in the BAISD Early Literacy Grant with 1st grade teachers, interventionists and literacy coaches.

Under the building’s Reading Goal -Create an objective specific to this work

**Objective:** 85% of all students will demonstrate reading proficiency by June 15, 2019 as measured by the state 3rd grade reading assessment.

**Strategy 1: 1st grade teacher leaders, Interventionists and Literacy Coach will participate in the BAISD Early Literacy Network**

**Category**: Literacy

**Tier:** 1

**How will the strategy work? How will the strategy be implemented?** The BAISD Early Literacy Consultant will collaborate with a network of 1st grade teachers and literacy coaches from across the two counties in a series of activities all based around the MAISA’s “K-3 Essential Instructional Practices in Early Literacy”

**Research Citations at the end of the linked document:**

<http://www.gomaisa.org/sites/default/files/K-3%20Literacy%20Essentials%203.2016.pdf#overlay-context=general-education-leadership-network>

**Activity 1:**  Summer 2017 Collaborative Learning Session

**Tier** 1

**Type**: Professional Learning and Teacher Collaboration

**Activity Phase**: Implementing

**Activity Description**: Using state-wide professional learning materials based on “K-3 Essential Instructional Practices in Early Literacy,” the BAISD Early Literacy Network on August 10, 2017 and January 17, 2018

**Begin Date**: August 10, 2017 and end date January 17, 2018

**Responsible Staff:** Principal, 1st grade teacher leader, interventionist and literacy coach

**Funding Source:** Title IIA

**Amount:** $120 stipend per attendee in August 10, 2017 and $100 sub-cost for January 17, 2018

**Activity 2:**  Classroom Visits/Learning Labs

**Tier** 1

**Type**: Professional Learning and Teacher Collaboration

**Activity Phase**: Getting Ready/Implementing

**Activity Description**: BAISD Early Literacy Coach Models, Co-Teaches or Observers for Network Teacher as other teachers, interventionist, literacy coach and building leader observe. Debriefing time about their observations as they relate to the Essential Practices is provided– three times for ½ day

**Begin Date**: October 9, 2017 **End Date**: May 18, 2018

**Responsible Staff: Principals and** BAISD Early Literacy Network Teacher Leaders

**Funding Source:** Title IIA

**Amount:** $60 per teacher x 3 half-days

**Strategy 2: Building Level Coaches will continue to enhance their coaching skills through professional learning, collaboration and practice with others.**

**Activity 1: Building Level Coaches Collaborative with BAISD and SISD**

Tier 1

**Type**: Enhancing Coaching Skills

**Activity Phase**: Implementing

**Activity Description:** BAISD Building Literacy Coaches meet every other Monday afternoon to build their own skills and support each other facilitated by SISD Early Literacy Coordinator

**Begin:**  September 11, 2017 End: May 18, 2018

**Responsible Staff:** BAISD Early Literacy Network Team and Building Literacy Coaches

**Funding:**  Title IIA Release time

Amount:

**Activity 2:**  BAISD Early Literacy Network’s Regional Partnership

**Tier** 1

**Type**: Professional Learning and Teacher Collaboration

**Activity Phase**: Getting Ready/Implementing

**Activity Description**: BAISD Early Literacy Network Building Literacy Coaches attend the larger K-12 Great Lakes Bay Literacy Network to network beyond their own ISD and gain K-12 perspective. Four Thursdays during the school year one in September, November, February and March

**Begin Date**: September 14, 2017 **End Date**: April 1, 2018

**Responsible Staff:** BAISD and SISD

**Funding Source:** Title IIA

**Amount:** $120 per teacher x 4 days